## Sheet1
ID | User/Technical Story | Priority | Sprint | Status
1 | Find library with 2D faces | Must | 1 | To be started
2 | As a user I want to scan my face to get an 2D image | Must | 1 | To be started
3 | Get facial point into XML file using web application | Must | 1 | To be started
4 | Use machine learning algorithm (potentially KNN) to trim library down to 30-40 faces that match user specified XML points | Must | 2 | To be started
5 | Match faces from library to XML files (the 30-40 chosen), in order to use machine learning algorithm | Must | 2 | To be started
6 | Do research on KNN and SVM to see which is better at finding 3-5 noses from the chosen 30-40 faces | Must | 2 | To be started
7 | As a user I want to select preffered faces | Must | 3 | To be started
8 | Calculate changes from the user's selected face | Must | 3 | To be started
#REF! | Get ID 1-3 on the python app | Must | 1 | To be started
#REF! | Get ID 4-6 on the python app | Must | 2 | To be started
#REF! | Get ID 7-8 on the python app | Must | 3 | To be started
#REF! | As a user I want to use special camera to get 3D model of face | Could have | TBD | To be started
| Budget | 0